## Landing Page Project
[7 empty] | Web Manager | Makes final decisions about new site features and content changes. They sign off on the landing page design and launch plans. They also coordinate maintenance and management tasks to keep the page operating smoothly.
R - Responsible | Completes the deliverable or task. | [5 empty] | Graphic Designer | Creates and chooses images and typefaces for the landing page and submits them to the Web Designer for approval. They also provide feedback on the landing page design and mockup.
A - Accountable | Makes final decisions and signs off on task completion. Only 1 per task. | [5 empty] | Web Developer | Supports the product team by writing the code that powers the site. They give feedback to the Web Designer on the landing page mockup. The Web Developer also helps set quality standards for the project.
C - Consulted | An advisor, stakeholder, or subject matter expert who offers guidance before an action is taken. | [5 empty] | Quality Assurance Tester | Reviews system specifications and runs quality tests for the new landing page. They run test scripts and review results, create reports, and document technical issues. These tests identify problems that the team can then resolve before launch.
I - Informed | Kept up to date on decisions made. | [5 empty] | Content Writer | Creates the written content that explains how Plant Pals works and helps potential customers sign up for the service. They give feedback to the Web Designer on the landing page mockup.
Plant Pals Landing Page | Web Manager | Graphic Designer | Web Developer | Quality Assurance Tester | Content Writer | Web Designer | Web Designer | Creates the landing page design, determining how the page looks and how customers interact with it. The Web Designer connects the creative and technical elements of the project, ensuring that the website is both attractive and functional. They report to the Web Manager, who makes final decisions on new site features.
Task/Deliverable
1. Design a landing page | A | C | I | I | I | R
2. Create a landing page mockup | A | C | C | I | C | R
3. Design image assets | I | R | I | I | C | A
4. Write content | A | I | I | I | R | I
5. Code the landing page | A |  | R | I |  | C
6. Test the landing page | A |  | C | R |  | C